## Sheet1
S. No. | Task – Sub-Task | Expected Completion Date | Current Status | Overall Project Status | 18.18% | Completed
1 | Create Github Repository | 2018-04-23 | Completed
2 | FPGA Board
2-a | Search and finalize an FPGA Board that can interface with Jupyter Notebook | 2018-05-01 | Completed
2-b | Purchase the FPGA Board online | 2018-05-02 | Completed
2-c | Learn how to use Vivado HLS Software | 2018-05-06 | Yet to start
2-d | Receive the FPGA Board | 2018-05-10 | Yet to start
2-e | Run a sample program made using Vivado on the FPGA Board | 2018-05-11 | Yet to start
2-f | Install python libraries on the FPGA board that are necessary for machine learning | 2018-05-11 | Yet to start
3 | Jupyter Notebook File
3-a | Import the VGG Model | 2018-05-02 | Completed
3-b | Finalize a list of Test Classes | 2018-05-03 | Pending
3-c | Download the Test Data | 2018-05-03 | Pending
3-d | Pre-process the Test Data | 2018-05-04 | Pending
3-e | Predict the Output Class | 2018-05-04 | Pending
3-f | Print the Run-time | 2018-05-04 | Pending
3-g | Print the Test Accuracy | 2018-05-04 | Pending
4 | FPGA Implementation of VGGNet
4-a | Design the Vivado HLS model for the project | 2018-05-13 | Yet to start
4-b | Generate Bitstream file | 2018-05-14 | Yet to start
4-c | Create TCL file | 2018-05-14 | Yet to start
4-d | Program the FPGA | 2018-05-14 | Yet to start
4-e | Run the Jupyter Notebook File on the FPGA | 2018-05-14 | Yet to start
4-f | Predict the Output Class | 2018-05-14 | Yet to start
4-g | Print the Run-time | 2018-05-14 | Yet to start
4-h | Print the Test Accuracy | 2018-05-14 | Yet to start